## Sheet1
SL.No | Task | Start Date | End Date | Duration | Dependencies
1 | Project Planning | 2024-07-19 | 2024-07-19 | 1 days
2 | Requirements Gathering | 2024-07-20 | 2024-07-20 | 1 days | project planning
3 | Design Contact List UI | 2024-07-20 | 2024-07-21 | 1 days | Project Planning,Requirements Gathering
4 | Database Design | 2024-07-21 | 2024-07-22 | 1 days | Project Planning
5 | Frontend Development | 2024-07-22 | 2024-07-22 | 1 days | Design Contact List UI,Database Design
6 | Backend Development | 2024-07-22 | 2024-07-23 | 1 days | Database Design
7 | Integration & Testing | 2024-07-23 | 2024-07-24 | 1 days | Frontend Development, Backend Development
8 | User Acceptance Testing | 2024-07-24 | 2024-07-25 | 1 days | Integration & Testing
9 | Final Adjustments | 2024-07-25 | 2024-07-26 | 1 days | User Acceptance Testing
10 | Deployment | 2024-07-26 | 2024-07-27 | 1 days | Final Adjustments
11 | Project Review | 2024-07-28 | 2024-07-28 | 1 days | Deployment